## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-17 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-23 | 2019-11-24 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123 | 114 | 105 | 96 | 87 | 78 | 69 | 60 | 51 | 42 | 33 | 24 | 15 | 6 | 0 | Ideal Burndown
|  |  | 160 | 5 | 4.5 | 9 | 12.5 | 9 | 0 | 0 | 1 | 9.5 | 10 | 11 | 8.5 | 0 | 0 | 0.5 | 5.5 | 7.5 | 8 | 10 | 7 | 1.5 | 3.5 | 4 | 10.5 | 6 | 0 | 0 | 0 | Remaining Hrs (Total)
Enable user to register | Design Business Logic | Jinfeng | 2 | 2019-11-08: 0.5; 2019-11-09: 0.5; 2019-11-10: 0.5; 2019-11-12: 0.5
| Design User Interface | Jinfeng | 1 | 2019-11-08: 0.5; 2019-11-11: 0.5
| Design database | Jinfeng | 1 | 2019-11-09: 0.5; 2019-11-11: 0.5
| Implement Back-End Code | Jinfeng | 11 | 2019-11-09: 2; 2019-11-10: 3; 2019-11-11: 2; 2019-11-12: 1; 2019-11-15: 1; 2019-11-16: 1; 2019-11-17: 1
| Complete Unit Testing | Jinfeng | 1 | 2019-11-17: 0.5; 2019-11-19: 0.5
| Complete Regression Testing | Jinfeng | 1 | 2019-11-17: 0.5; 2019-11-19: 0.5
| Write Documentation | Jinfeng | 1 | bar: 2019-11-19
Enable user to open new account | Design Business Logic | Jinfeng | 1 | 2019-11-08: 0.5; 2019-11-09: 0.5
| Design User Interface | Jinfeng | 2 | 2019-11-08: 0.5; 2019-11-10: 0.5; 2019-11-11: 0.5; 2019-11-12: 0.5
| Design database | Jinfeng | 1 | 2019-11-10: 0.5; 2019-11-11: 0.5
| Implement Back-End Code | Jinfeng | 11 | 2019-11-10: 3; 2019-11-11: 4; 2019-11-12: 2; 2019-11-16: 1; 2019-11-17: 1
| Complete Unit Testing | Jinfeng | 1 | 2019-11-17: 0.5; 2019-11-18: 0.5
| Complete Regression Testing | Jinfeng | 1 | bar: 2019-11-18
| Write Documentation | Jinfeng | 1 | 2019-11-22: 0.5; 2019-11-24: 0.5
deposit money | Design Business Logic | Lijuan | 1 | 2019-11-08: 0.5; 2019-11-11: 0.5
| Design User Interface | Lijuan | 2 | 2019-11-08: 0.5; 2019-11-09: 0.5; 2019-11-10: 0.5; 2019-11-12: 0.5
| Design database | Lijuan | 1 | 2019-11-08: 0.5; 2019-11-10: 0.5
| Implement Back-End Code | Lijuan | 11 | 2019-11-11: 3; 2019-11-12: 4; 2019-11-16: 1; 2019-11-17: 1; 2019-11-18: 1; 2019-11-19: 1
| Complete Unit Testing | Lijuan | 1 | 2019-11-18: 0.5; 2019-11-19: 0.5
| Complete Regression Testing | Lijuan | 1 | 2019-11-23: 0.5; 2019-11-25: 0.5
| Write Documentation | Lijuan | 1 | 2019-11-24: 0.5; 2019-11-26: 0.5
Closing existing accounts | Design Business Logic | Lijuan | 2 | 2019-11-08: 0.5; 2019-11-09: 0.5; 2019-11-10: 0.5; 2019-11-11: 0.5
| Design User Interface | Lijuan | 1 | 2019-11-08: 0.5; 2019-11-12: 0.5
| Design database | Lijuan | 1 | 2019-11-08: 0.5; 2019-11-11: 0.5
| Implement Back-End Code | Lijuan | 11 | 2019-11-16: 2; 2019-11-17: 3; 2019-11-18: 2; 2019-11-19: 2; 2019-11-24: 1; 2019-11-26: 1
| Complete Unit Testing | Lijuan | 1 | 2019-11-25: 0.5; 2019-11-26: 0.5
| Complete Regression Testing | Lijuan | 1 | 2019-11-25: 0.5; 2019-11-26: 0.5
| Write Documentation | Lijuan | 1 | bar: 2019-11-27
Transfer between accounts - one time or recurring | Design Business Logic | Zhekai | 1 | 2019-11-08: 0.5; 2019-11-11: 0.5
| Design User Interface | Zhekai | 0.5 | 2019-11-08: 0.25; 2019-11-09: 0.25
| Design database | Zhekai | 1 | 2019-11-08: 0.5; 2019-11-11: 0.5
| Implement Back-End Code | Zhekai | 15 | 2019-11-16: 3; 2019-11-17: 1; 2019-11-18: 2; 2019-11-19: 3; 2019-11-23: 1; 2019-11-24: 1
| Complete Unit Testing | Zhekai | 1 | 2019-11-18: 0.5; 2019-11-24: 0.5
| Complete Regression Testing | Zhekai | 1 | 2019-11-18: 0.5; 2019-11-25: 0.5
| Write Documentation | Zhekai | 0.5 | 2019-12-01: 0.5
Set up recurring or one-time Bill payment for external payees | Design Business Logic | junyan | 1 | 2019-11-08: 0.5; 2019-11-09: 0.5
| Design User Interface | junyan | 0.5 | 2019-11-08: 0.5
| Design database | junyan | 1 | 2019-11-10: 0.5; 2019-11-11: 0.5
| Implement Back-End Code | junyan | 15 | 2019-11-23: 2; 2019-11-24: 2; 2019-11-25: 2; 2019-11-26: 3; 2019-11-29: 2; 2019-11-30: 2; 2019-12-01: 2
| Complete Unit Testing | junyan | 1 | 2019-11-26: 0.5; 2019-11-29: 0.5
| Complete Regression Testing | junyan | 1 | 2019-11-26: 0.5; 2019-12-01: 0.5
| Write Documentation | junyan | 0.5 | 2019-11-26: 0.5
View and search Transactions - for credits/debits/checks/fees - up to last 18 months | Design Business Logic | Zhekai | 1 | 2019-11-08: 0.5; 2019-11-10: 0.5
| Design User Interface | Zhekai | 0.5 | 2019-11-08: 0.5
| Design database | Zhekai | 1 | 2019-11-08: 0.5; 2019-11-10: 0.5
| Implement Back-End Code | Zhekai | 15 | 2019-11-16: 1; 2019-11-18: 1; 2019-11-23: 2; 2019-11-24: 2; 2019-11-25: 2; 2019-11-27: 2; 2019-11-29: 1; 2019-11-30: 2; 2019-12-01: 2
| Complete Unit Testing | Zhekai | 1 | bar: 2019-11-28
| Complete Regression Testing | Zhekai | 1 | 2019-11-28: 0.5; 2019-12-02: 0.5
| Write Documentation | Zhekai | 0.5 | 2019-12-02: 0.5
Add transactions - such as manual refunds on fees | Design Business Logic | junyan | 1 | 2019-11-08: 0.5; 2019-11-10: 0.5
| Design User Interface | junyan | 0.5 | 2019-11-08: 0.5
| Design database | junyan | 1 | 2019-11-16: 0.5; 2019-11-17: 0.5
| Implement Back-End Code | junyan | 15 | 2019-11-17: 1; 2019-11-18: 2; 2019-11-25: 2; 2019-11-26: 3; 2019-11-27: 4; 2019-12-02: 3
| Complete Unit Testing | junyan | 1 | bar: 2019-12-01
| Complete Regression Testing | junyan | 1 | bar: 2019-12-02
| Write Documentation | junyan | 0.5 | 2019-12-02: 0.5
Deploy API to AWS as Docker Containers in Amazon Containers or EKS | Configurationg environment | Jinfeng | 0.5 | 2019-11-08: 0.5
| Deply API to AWS | Jinfeng | 2 | 2019-11-08: 0.5; 2019-11-10: 0.5; 2019-11-11: 0.5; 2019-11-12: 0.5
| Complete Unit Testing | Jinfeng | 0.5 | 2019-12-02: 0.5
| Complete Regression Testing | Jinfeng | 0.5 | 2019-12-01: 0.5
| Write Documentation | Jinfeng | 0.5 | 2019-12-01: 0.5
Deploy API to AWS in an Auto Scaled EC2 Cluster with Load Balancer | Configurationg environment | Lijuan | 0.5 | 2019-11-08: 0.1; 2019-11-09: 0.1; 2019-11-10: 0.1; 2019-11-11: 0.1; 2019-11-12: 0.1; 2019-12-01: 0.5
| Deply API to AWS | Lijuan | 2 | 2019-12-01: 2
| Complete Unit Testing | Lijuan | 0.5 | 2019-12-01: 0.5
| Complete Regression Testing | Lijuan | 0.5 | 2019-12-01: 0.5
| Write Documentation | Lijuan | 0.5
Team:
Junyan | 10 hours / Week
Jifeng | 10 hours / Week
LIjuan | 10 hours / Week
Zhekai | 10 hours / Week
Total Available Hours During Sprint: | 160